## Product Backlog
US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
1 | As an administrator, I want to configure an online MCQ assessment with a time limit so candidates can complete a controlled examination. | Must | Assessment/database models | Harsha Vardhan B S | Completed
2 | As a candidate, I want pre-assessment camera and face validation so the monitoring setup is verified before the exam. | Must | Camera service; OpenCV | Harsha Vardhan B S | Completed
3 | As an invigilator, I want browser activity and focus events captured so suspicious behavior can be reviewed. | Must | Browser monitoring; event logging | Harsha Vardhan B S | Completed
4 | As an invigilator, I want no-face and multiple-face events recorded so integrity risks can be identified. | Must | Camera service; OpenCV | Harsha Vardhan B S | Completed
5 | As an invigilator, I want an integrity score and risk label generated from events so sessions can be classified consistently. | Must | Violation weights; session data | Harsha Vardhan B S | Completed
6 | As an analyst, I want session data summarized with Pandas and visualizations so examination behavior can be understood. | Should | Session/violation records | Harsha Vardhan B S | Completed
7 | As an analyst, I want K-Means clustering of sessions so behavioral groups can be explored. | Should | Pandas/NumPy; scikit-learn | Harsha Vardhan B S | Completed
8 | As an invigilator, I want an AI-assisted integrity report with fallback so a readable report can be produced reliably. | Could | LangChain; analytics | Harsha Vardhan B S | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Original Estimate (Hours) | Effort (Hours) | Team Member | Activity | Status
1 | 1 | Design assessment/session flow and database entities | 2026-08-17 | 6 | 6 | Harsha Vardhan | Development | Completed
2 | 2 | Implement MCQ UI, timer, navigation and answer handling | 2026-08-18 | 10 | 10 | Harsha Vardhan | Development | Completed
2 | 3 | Implement answer autosave, review and submission workflow | 2026-08-19 | 8 | 8 | Harsha Vardhan | Development | Completed
3 | 4 | Implement tab switch, focus loss, copy/paste and browser monitoring | 2026-08-20 | 10 | 10 | Harsha Vardhan | Development | Completed
4 | 5 | Implement camera validation and face monitoring using OpenCV | 2026-08-21 | 10 | 10 | Harsha Vardhan | Development | Completed
5 | 6 | Implement integrity score, deductions and risk classification | 2026-08-24 | 8 | 8 | Harsha Vardhan | Development | Completed
6 | 7 | Build Pandas analytics and Matplotlib/Seaborn visualizations | 2026-08-25 | 8 | 8 | Harsha Vardhan | Data Analysis | Completed
7 | 8 | Implement K-Means clustering and cohort risk profiling | 2026-08-26 | 8 | 8 | Harsha Vardhan | Data Science | Completed
8 | 9 | Implement LangChain integrity report generation with fallback | 2026-08-27 | 6 | 6 | Harsha Vardhan | AI Integration | Completed
5 | 10 | Validate low/medium/high-risk synthetic sessions | 2026-08-28 | 6 | 6 | Harsha Vardhan | Testing | Completed

## Stand up Meeting
Sprint Day | Date | Impediments | Action Taken
1 | 2026-08-17 | Initial integration of assessment, monitoring and database components. | Set up project structure, reviewed dependencies and defined integration sequence.
2 | 2026-08-18 | Assessment state needed reliable synchronization. | Implemented autosave/state handling and verified navigation flow.
3 | 2026-08-20 | Browser/fullscreen events needed to avoid duplicate logging. | Separated browser-monitor events from session-level fullscreen handling.
4 | 2026-08-21 | Camera service compatibility and validation required refinement. | Restored canonical camera service flow and verified one-face validation.
5 | 2026-08-25 | Analytics needed consistent session-level features. | Prepared Pandas summaries and visualization inputs.
6 | 2026-08-26 | Cluster interpretation required normalized behavioral features. | Applied K-Means to session features and documented cohort interpretation.
7 | 2026-08-28 | AI reporting needed reliable output if external model access fails. | Added deterministic fallback and validated representative risk cases.

## Retrospection
Sprint | Start Date | End Date | What Went Well | What Could Be Improved | Continue Doing | Action Taken
1 | 2026-08-17 | 2026-08-21 | Core assessment and monitoring components were integrated. | Dependency compatibility and camera-service regression required extra effort. | Validate each module after integration. | Use Python 3.12-compatible environment and restore canonical shared services.
2 | 2026-08-24 | 2026-08-28 | Integrity scoring, analytics, clustering and reporting were integrated. | UI/debugging issues showed the need for frequent browser-level validation. | Use incremental smoke tests with representative sessions. | Validate synthetic low/medium/high-risk cases and integration flows.