## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Harsha Vardhan B S | 2026-08-21 | Camera service regression caused missing save_frame_as_temp, release_instance and check_available methods. | Sprint 1 | Harsha Vardhan B S | Maintainability | Restored canonical camera service implementation and revalidated lifecycle methods. | 2026-08-21 | Closed | Shared service API restored.
2 | Harsha Vardhan B S | 2026-08-27 | Assessment page rendered a blank body while scripts appeared in the document head, causing a white screen. | Sprint 2 | Harsha Vardhan B S | Standards | Inspected template inheritance and restored the canonical session template content structure. | 2026-08-27 | Closed | Assessment content rendered inside base template content block.
3 | Harsha Vardhan B S | 2026-08-27 | Local monitoring POST requests were blocked by CSRF protection during local demonstration. | Sprint 2 | Harsha Vardhan B S | Logical | Temporarily disabled CSRF for local demo configuration and verified monitoring requests. | 2026-08-27 | Closed | Production should retain CSRF protection.
4 | Harsha Vardhan B S | 2026-08-26 | Face-detection constants were defined but detection used hard-coded values. | Sprint 2 | Harsha Vardhan B S | Logical | Aligned detection with configured scale factor, neighbor threshold and minimum face size. | 2026-08-26 | Closed | Configuration is now used for tuning.
5 | Harsha Vardhan B S | 2026-08-28 | Python dependency compatibility caused installation issues in a newer Python environment. | Sprint 2 | Harsha Vardhan B S | Maintainability | Created Python 3.12 virtual environment and installed requirements successfully. | 2026-08-28 | Closed | venv312 excluded through .gitignore.